DAILY WORK REPORT

| PROJECT | SC 93 Widening, Phase 2 | CONTRACT NO. | P-0293-24 |
| --- | --- | --- | --- |
| LOCATION | Clemson, SC | DATE | Thursday, October 15, 2026 |
| PRIME CONTRACTOR | Palmetto Site Works | REPORT NO. | 42 |
| INSPECTOR | Tyler Bowles | WORKERS ON SITE | 10 |

WEATHER

| AM | PM | 7 AM | Noon | 4 PM | High / low | Precip. | Wind |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Clear | Partly cloudy | 55 F | 71 F | 76 F | 78 / 52 F | 0.00 in | 9 mph |

Weather from Open-Meteo for 34.6834, -82.8374.

CONTRACTOR FORCES

| Contractor | Classification | No. | Hours |
| --- | --- | --- | --- |
| Palmetto Site Works | Foreman | 1 | 8 |
| Palmetto Site Works | Laborer | 4 | 8 |
| Palmetto Site Works | Operator | 2 | 8 |
| Upstate Concrete | Finisher | 3 | 6 |

EQUIPMENT

| Description | No. | Status | Hours |
| --- | --- | --- | --- |
| CAT 320 excavator | 1 | Working |  |
| Skid steer | 1 | Working |  |
| Smooth drum roller | 1 | Idle |  |

WORK PERFORMED

| Description | Location | Quantity |
| --- | --- | --- |
| Excavated and backfilled the storm drain trench from station 12+50 to 14+00, about 150 linear feet of 24 inch RCP installed | Sta. 12+50 to 14+00 | 150 linear feet |
| Poured the curb and gutter on the east side, about 18 cubic yards | east side | 18 cubic yards |

MATERIALS RECEIVED

Received six loads of number 57 stone.

TESTS AND INSPECTIONS

Ran a slump test on the second truck, four inch slump, and made one set of cylinders.

Nuclear gauge density tests on the trench backfill all passed.

VISITORS

Tom Reed from the county came by at 2 PM to look at the drainage.

DELAYS, PROBLEMS AND RFIS

Lost about an hour in the morning waiting on the first concrete truck.

Found an unmarked water line at station 13+20, contractor stopped and called the utility, we need an RFI.

SAFETY

Trench box was in place all day, one worker without a vest, talked to the foreman about it.

REMARKS

Weather on site: Weather was clear and cool in the morning, warming up after lunch.

October 15th, Highway 93 widening near Clemson.

CERTIFICATION

I certify that this report is a true record of the work and conditions observed.

| INSPECTOR __________________________________ ____________ Signature Date | REVIEWED BY (RESIDENT ENGINEER) __________________________________ ____________ Signature Date |
| --- | --- |

PHOTOGRAPHS

| Photo 1. 10:42 AM. Open storm drain trench with trench box in place and excavator working near Sta. 13+00. | Photo 2. 2:18 PM. Fresh curb and gutter on the east side after the afternoon pour. |
| --- | --- |